## 1. Executive Summary
DMV Permit Prep App — Master Plan
Best-to-worst state launch plan with content, marketing, and revenue model
Total addressable market: 51 US jurisdictions, ~17M new permit/license tests/year
THE VISION
• ONE engine — 51 content packs. Build the iOS test-prep engine once; ship state-specific question banks as separate App Store SKUs.
• PERFECT means principled, not bloated. Three perfect features beat ten mediocre ones. Procreate Pocket model: do ONE thing extremely well, charge a fair one-time price.
• PRIVACY-FIRST is the wedge. No accounts, no cloud, no ads, no tracking. Free competitors (DMV Genie, iDriverManual) are ad-bloated. Premium ones are subscriptions. Buy-once $4.99 + no surveillance = differentiator.
• MULTILINGUAL is the moat. California's official test is in 24+ languages. Florida just removed Spanish/Creole testing — bilingual STUDY app for Florida is a generational gap.
• STATE-SPECIFIC is the table-stakes. Real agency names (DMV vs DPS vs DDS vs MVA vs RMV), real fines, real local rules. No 'generic permit prep' nonsense.
YEAR 1 TARGETS
Metric | Target | Stretch | Notes
States shipped | 4 (FL, TX, CA, NY) | 10 | Tier 1 covers ~33% of US population
Total downloads | 50,000 | 150,000 | Apple Search Ads + TikTok content + driving-school partnerships
Paid conversion | 8–12% | 15% | Industry benchmark for paid utility apps
Avg revenue per state | $30K–80K | $200K | Tier 1 states; Tier 2/3 lower individually but cumulative
Year 1 cumulative revenue | $200K–400K | $1M+ | Compounds as more state SKUs ship
Year 2 (all 51 SKUs) | $500K–1M | $2M+ | Engine built; only content production scaling

## 2. State-by-State Plan
# | State | Code | Pop (M) | Agency | # Qs | Pass % | Time (min) | Languages on Real Test | Online Test? | Tier | Launch Order | Yr 1 Est. Rev ($K) | State-Specific Notes
1 | Florida | FL | 22.9 | FLHSMV | 50 | 80% | – | EN ONLY | Yes | T1 | 1 | 160 | Verified: 50 Qs, 80%, Class E exam. ENGLISH-ONLY since Feb 6 2026 — huge bilingual STUDY app gap (Spanish/Creole speakers).
2 | Texas | TX | 30.5 | DPS | 30 | 70% | 60 | EN, ES | Yes | T1 | 2 | 180 | Verified: 30 Qs, 70%, two parts (15 signs + 15 traffic laws). Big Spanish market. ITAD course required for adults 18-24.
3 | New York | NY | 19.5 | DMV | 20 | 70% | 30 | EN, ES, ZH, RU, KO, FR, IT, JA, PL, EL, AR, BN, UR | Yes | T1 | 3 | 130 | Easiest test format (20 Qs, 70%). 13 languages. Big NYC immigrant audience.
4 | California | CA | 39 | DMV | 36 | 83% | – | EN, ES, ZH, VI, KO, RU, AR, JA, FR, IT, PT, TL, AM, HI, KM, HY, FA, PA, TH, HE, EL, ID, IL, NE | Yes | T1 | 4 | 220 | Largest market. Highest competition. Multilingual is the moat (24+ languages on actual test).
5 | Pennsylvania | PA | 13 | PennDOT | 18 | 83% | 60 | EN, ES, AR, KM, ZH, RU, KO, VI | No | T2 | 5 | 75 | Short test. Spanish + Mandarin needed. PennDOT terminology specific.
6 | Illinois | IL | 12.6 | Sec State | 35 | 80% | – | EN, ES, PL, ZH, RU, KO, AR | No | T2 | 6 | 85 | Sec of State runs DMV. Polish + Spanish significant. Chicago suburbs primary.
7 | Ohio | OH | 11.8 | BMV | 40 | 75% | – | EN, ES, SO, AR | No | T2 | 7 | 60 | BMV = Bureau of Motor Vehicles. Smaller language need. Somali community in Columbus/Cincinnati.
8 | Georgia | GA | 11.1 | DDS | 40 | 75% | – | EN, ES, KO, ZH, VI, FR, RU, JA | No | T2 | 8 | 70 | DDS = Dept of Driver Services. Atlanta has large Korean and Vietnamese communities.
9 | North Carolina | NC | 10.8 | DMV | 25 | 80% | – | EN, ES, ZH, KO, VI, AR, FR | No | T2 | 9 | 55 | Charlotte/Raleigh growing immigrant markets. 80% pass.
10 | Michigan | MI | 10 | SOS | 50 | 80% | – | EN, ES, AR | No | T2 | 10 | 50 | SOS = Sec of State. Dearborn has largest Arab-American community in US — Arabic critical.
11 | New Jersey | NJ | 9.3 | MVC | 50 | 80% | 30 | EN, ES, AR, FR, JA, KO, PL, PT, ZH, IT, RU, GU, HI | No | T2 | 11 | 60 | MVC = Motor Vehicle Commission. Hindu/Gujarati community significant. Polish near NYC.
12 | Virginia | VA | 8.7 | DMV | 35 | 80% | – | EN, ES, KO, VI, AR, ZH, FA, FR, RU | No | T2 | 12 | 45 | DC suburbs = high educated immigrant population. NoVA tech professionals.
13 | Washington | WA | 7.8 | DOL | 25 | 80% | – | EN, ES, ZH, KO, VI, RU, SO, UK | No | T2 | 13 | 40 | DOL = Dept of Licensing. Seattle Russian/Ukrainian + tech immigrants.
14 | Arizona | AZ | 7.4 | MVD | 30 | 80% | – | EN, ES | No | T2 | 14 | 40 | MVD. Phoenix growing fast. Spanish primary. No drivers ed required for adults.
15 | Massachusetts | MA | 7.1 | RMV | 25 | 72% | 25 | EN, ES, PT, ZH, RU, FR, VI, KO, AR, IT, KM, JA, KO, SQ | No | T2 | 15 | 35 | RMV = Registry of Motor Vehicles. Most languages of any state (35+). Portuguese strong.
16 | Tennessee | TN | 7.1 | DOS | 30 | 70% | – | EN, ES | No | T2 | 16 | 30 | DOS = Dept of Safety. Nashville Hispanic growing. 70% pass = easier.
17 | Indiana | IN | 6.9 | BMV | 50 | 84% | – | EN, ES, ZH, KO, MY, AR | No | T2 | 17 | 30 | BMV. Burmese community in Indianapolis significant.
18 | Missouri | MO | 6.2 | DOR | 25 | 80% | – | EN, ES | No | T2 | 18 | 25 | DOR = Dept of Revenue. Limited language options.
19 | Maryland | MD | 6.2 | MVA | 25 | 88% | 30 | EN, ES, ZH, KO, FR, RU, VI | No | T2 | 19 | 30 | MVA. DC suburbs. High pass score (88%) - hard test.
20 | Wisconsin | WI | 5.9 | DMV | 50 | 80% | – | EN, ES, HMN | No | T2 | 20 | 25 | Hmong community in Milwaukee/Wausau — Hmong language unique to WI/MN.
21 | Colorado | CO | 5.9 | DMV | 25 | 80% | 30 | EN, ES | No | T3 | 21 | 25 | Denver growing tech market. Spanish primary.
22 | Minnesota | MN | 5.8 | DVS | 40 | 80% | – | EN, ES, SO, HMN, OM, KAR | No | T3 | 22 | 25 | DVS. Twin Cities = largest Somali community in US. Karen refugees.
23 | South Carolina | SC | 5.5 | DMV | 30 | 80% | – | EN, ES | No | T3 | 23 | 20 | Limited language need.
24 | Alabama | AL | 5.1 | ALEA | 30 | 80% | – | EN, ES | No | T3 | 24 | 18 | Small market.
25 | Louisiana | LA | 4.6 | OMV | 40 | 80% | – | EN, ES, VI | No | T3 | 25 | 18 | OMV. Vietnamese in New Orleans area.
26 | Kentucky | KY | 4.5 | KYTC | 40 | 80% | – | EN, ES | No | T3 | 26 | 18
27 | Oregon | OR | 4.2 | DMV | 35 | 80% | 30 | EN, ES, RU, ZH, VI, KO, JA | No | T3 | 27 | 20 | Portland Russian community.
28 | Oklahoma | OK | 4.1 | DPS | 25 | 80% | – | EN, ES, VI | No | T3 | 28 | 15
29 | Connecticut | CT | 3.6 | DMV | 25 | 80% | 30 | EN, ES, PL | No | T3 | 29 | 18
30 | Utah | UT | 3.4 | DLD | 25 | 80% | – | EN, ES | No | T3 | 30 | 15 | DLD. Tongan/Samoan communities.
31 | Iowa | IA | 3.2 | DOT | 35 | 80% | – | EN, ES | No | T3 | 31 | 12
32 | Nevada | NV | 3.2 | DMV | 50 | 80% | 30 | EN, ES, ZH, TL | No | T3 | 32 | 18 | Las Vegas Filipino community.
33 | Arkansas | AR | 3.1 | DFA | 25 | 80% | – | EN, ES | No | T3 | 33 | 10
34 | Mississippi | MS | 2.9 | DPS | 30 | 80% | – | EN, ES | No | T3 | 34 | 10
35 | Kansas | KS | 2.9 | DOR | 25 | 80% | – | EN, ES | No | T3 | 35 | 10
36 | New Mexico | NM | 2.1 | MVD | 25 | 75% | – | EN, ES | No | T3 | 36 | 10 | Heavy Spanish market.
37 | Nebraska | NE | 2 | DMV | 25 | 80% | – | EN, ES | No | T3 | 37 | 8
38 | Idaho | ID | 2 | ITD | 40 | 75% | – | EN, ES | No | T3 | 38 | 8 | ITD = Idaho Transportation Dept.
39 | West Virginia | WV | 1.8 | DMV | 25 | 80% | – | EN | No | T3 | 39 | 6
40 | Hawaii | HI | 1.5 | DOT | 30 | 80% | – | EN, ES, JA, ZH, KO, TL, IL | No | T3 | 40 | 12 | Filipino + Japanese huge. Per-capita iPhone strong.
41 | New Hampshire | NH | 1.4 | DMV | 40 | 80% | – | EN, ES, FR | No | T3 | 41 | 6
42 | Maine | ME | 1.4 | BMV | 40 | 75% | – | EN, ES, FR, SO | No | T3 | 42 | 5 | Somali in Lewiston/Portland.
43 | Montana | MT | 1.1 | MVD | 33 | 80% | – | EN, ES | No | T3 | 43 | 5
44 | Rhode Island | RI | 1.1 | DMV | 25 | 80% | 30 | EN, ES, PT | No | T3 | 44 | 6 | Portuguese community.
45 | Delaware | DE | 1 | DMV | 25 | 80% | – | EN, ES | No | T3 | 45 | 5
46 | South Dakota | SD | 0.9 | DMV | 25 | 80% | – | EN, ES | No | T3 | 46 | 3
47 | North Dakota | ND | 0.8 | DOT | 25 | 75% | – | EN, ES | No | T3 | 47 | 3
48 | Alaska | AK | 0.7 | DMV | 20 | 80% | – | EN, ES | No | T3 | 48 | 3
49 | Vermont | VT | 0.6 | DMV | 20 | 80% | – | EN, ES, FR | No | T3 | 49 | 2
50 | Wyoming | WY | 0.6 | DOT | 25 | 80% | – | EN, ES | No | T3 | 50 | 2
51 | Washington DC | DC | 0.7 | DMV | 25 | 80% | 30 | EN, ES, AM, ZH, FR, KO, VI | No | T3 | 51 | 8 | Amharic significant (Ethiopian community).
| TOTAL Y1 TARGET |  | 335.5 | [8 empty] | 1789

## 3. Tier 1 Launch Detail
Tier 1 — First 4 Months: FL → TX → CA → NY
Florida ships first as the master template. Each subsequent state takes ~1 week of content work after engine is proven.
Week | State | Phase | Build Tasks | Content Tasks | Marketing Tasks | Output / Decision Gate
1 | Florida | Foundation | iOS shell, onboarding, test engine architecture, local SQLite schema, StoreKit 2 setup | Pull FLHSMV handbook (public domain). Outline 12 question categories: signs, ROW, parking, alcohol/DUI, fines, license types, etc. | Reserve Florida-specific App Store name and bundle ID. Domain name registered. | Clickable prototype with 50 questions. Engine architecture frozen.
2 | Florida | Question Engine | Practice mode, timed mock-test mode, weak-area tracker, wrong-answer review with explanations | Write 250–400 questions with explanations + handbook references. Tag by category. Spanish translation pass for STUDY mode (not test mode — FL is English-only test). | Set up TikTok Florida driver content account. Plan 5 viral hooks. | Functional MVP with full Florida question bank.
3 | Florida | Polish + Pkg | Progress dashboard, audio narration (AVSpeechSynthesizer), bookmarks, parent/teen mode toggle, App Store screenshots, accessibility (Dynamic Type, VoiceOver) | Accuracy review pass with actual Florida test takers (your network in FL). Final question polish. | Landing page live. Pre-launch waitlist email capture. | App Store-ready submission build.
4 | Florida | Launch + Validate | TestFlight beta with 50 users, App Store submission, iterate from review feedback | Add any questions reviewers say got missed. | $300 Apple Search Ads test on "Florida permit test" keywords. 5 TikTok videos posted. Email waitlist. | GATE: Did >5% of installs convert to purchase? If YES → expand. If NO → diagnose before TX.
5 | Texas | Re-skin + Content | Localize to Texas terminology (DPS not DMV, vision/hearing test specifics). Add bilingual full Spanish test mode. | Pull TX Driver Handbook. Write 300+ TX-specific questions in 2 sections (signs / traffic laws) — match real exam format. | TikTok Texas account. Hispanic-targeted Spanish-language Instagram content. | Texas v1 in TestFlight.
6 | Texas | Launch | Submit to App Store. Set up bilingual UI toggle. | TX Spanish translation accuracy pass with native speaker. | $500 Apple Search Ads with English + Spanish keyword sets. 10 TikTok videos. | Texas live in App Store.
7 | California | Re-skin Foundation | Add multi-language framework: ZH, VI, KO, RU, AR (top 5 after EN/ES per CA DMV data). | Pull CA DMV handbook. Write 400+ questions covering CA-specific (left-turn lane rules, freeway etiquette, DUI specifics). | Identify CA driving school partnerships in LA, SF, Sacramento (target 3-5 pilots). | CA v1 base + 7 languages.
8 | California | Bigger Languages | Add Tagalog (TL) for Filipino market, Japanese (JA) for Bay Area. | Translation QA. Verify CA-specific traffic terms. | Driving school outreach: free school-license tier. | CA v1 with 9 languages ready.
9 | California | Polish | Audio narration in all supported languages (premium feature). | Final accuracy pass. Add Persian and Armenian if budget allows (LA market). | Spanish-language TikTok creator outreach. | CA Store-ready.
10 | California | Launch | App Store submission. Apple Search Ads bilingual. | Monitor download mix by language to inform Tier 2 priorities. | $1,000 ad budget. Driving school deployment. | CA live. Decide on next 6 states based on language uptake data.
11 | New York | Re-skin | NY has only 20 questions / 70% — recalibrate test format. Add ZH + RU (NYC populations). | NY-specific content: NYC-specific rules, expressway etiquette, parking nightmares, snow rules. | NYC immigrant community outreach. Brooklyn / Queens DMV school partnerships. | NY v1 build.
12 | New York | Launch | NY App Store submission. | Translation QA. | $500 ad budget. | NY live. End of Tier 1 — 4 states, ~33% of US population covered.

## 4. Product Architecture
What "Perfect" Means — Feature Architecture
Three categories: Core (must-have v1), Premium (nice-to-have v1), Future (v2+).
Tier | Feature | Why It Matters | Build Effort | Differentiator vs DMV Genie? | V1 / V2
CORE | Practice mode (unlimited Qs) | Foundational. Without this, no app. | LOW | – | V1
CORE | Mock test mode (matches state format) | Simulates real exam exactly: question count, time limit, sections. | LOW | Most apps fake this | V1
CORE | Wrong-answer review with handbook ref | Each wrong answer links to handbook section. Teaching, not just testing. | LOW | YES — most apps skip | V1
CORE | Category breakdown (signs, ROW, etc.) | Drive practice toward weak areas, not random. | LOW | YES | V1
CORE | Audio narration (text-to-speech) | Critical for ESL learners, dyslexia, commute studying. | LOW | YES — major | V1
CORE | Offline-first (zero network needed) | Privacy + works in DMV waiting room. Free apps need network for ads. | LOW | YES — wedge | V1
CORE | No accounts, no cloud, no tracking | Privacy positioning is THE differentiator. Free apps track everything. | LOW | YES — core moat | V1
CORE | State-accurate terminology + fines | Real agency name (DPS not DMV in TX). Real fine amounts. Free apps say "consult your state". | MED | YES | V1
CORE | Bilingual (EN + state primary lang) | CA needs ES at minimum. FL needs ES STUDY mode (test is EN-only). TX bilingual full. | MED | YES — major | V1
CORE | Test-day checklist + what to bring | Last-mile: what documents, what to expect, what NOT to wear. | LOW | Some have this | V1
PREMIUM | Spaced repetition algorithm (SM-2) | Re-tests weak areas with intelligent timing. Zutobi has this — must match. | MED | Match competitors | V1
PREMIUM | Daily streak + gamification | Habit formation. Re-engagement. | MED | Match competitors | V1
PREMIUM | Parent/teen mode (parent monitors) | Parents are the buyers; teens are the users. Visibility = repeat purchases for sibs. | MED | YES — most lack | V1
PREMIUM | Printable cheat sheet (PDF export) | Last-night-before-test review. Tactile reassurance. | LOW | Some have | V1
PREMIUM | Multi-language UI (CA: 9+ langs) | CA real test is in 24 languages. Match top 9 to capture immigrant market. | HIGH | YES — moat at scale | V1
PREMIUM | Disability accommodations | Dyslexia-friendly font (OpenDyslexic), large-text mode, full VoiceOver support. | MED | YES — almost none | V1
PREMIUM | Apple Watch glance widget | Question-of-the-day on watch. Daily reminder. | MED | YES — none have | V2
FUTURE | CDL test prep (Class A, B, C) | Adjacent product. Truckers pay more. Specialized SKU per state. | HIGH | New category | V2
FUTURE | Motorcycle endorsement | Adjacent product. Riders are passionate buyers. | MED | New category | V2
FUTURE | Behind-the-wheel road test prep | Video content + checklist for actual road test. | HIGH | Differentiated | V2
FUTURE | AI tutor chat (LLM-powered) | Ask questions in natural language; get handbook-grounded answers. | HIGH | YES — none have | V2
FUTURE | Driving school B2B portal | Schools license bulk seats. Recurring revenue. | HIGH | YES | V2

## 5. Pricing Strategy
Pricing — One-Time Purchase Model
Buy-once, no subscription. Bundles to capture multi-state buyers and families.
Product SKU | Description | Price | Apple Cut (30%/15%) | Net per Sale | Notes
Per-state app (Tier 1) | FL, TX, CA, NY — full bilingual + premium | 6.99 | 2.097 | 4.893 | Tier 1 = highest content investment
Per-state app (Tier 2) | PA, IL, OH, GA, NC, MI, NJ, VA, WA, AZ, MA + 5 | 5.99 | 1.797 | 4.193 | Standard tier
Per-state app (Tier 3) | All remaining 35 states | 4.99 | 1.497 | 3.493 | Smaller markets, simpler content
"Family Pack" (4 users) | One purchase covers up to 4 family members | 12.99 | 3.897 | 9.093 | For households with multiple teens
Multi-state bundle (any 3) | Pick any 3 states (snowbirds, recent movers) | 13.99 | 4.197 | 9.793 | Florida-NY-CA bundle is biggest
"Lifetime Pro" upgrade (per state) | Unlocks AI tutor, audio in all langs, motorcycle module | $2.99 IAP | – | – | Optional add-on after purchase
CDL Class A/B/C add-on | Commercial license prep (V2) | $9.99 IAP | – | – | Truckers willing to pay more
Driving school license (B2B) | School-wide seat license, 50 students/yr | $299/yr per school | – | – | V2 — recurring revenue
Spanish-only edition (FL) | Special FL-only product: pure Spanish study mode for English test | 7.99 | 2.397 | 5.593 | Targeted at recent immigrants who need to learn material in Spanish to pass English test

## 6. Marketing Playbook
Marketing — Distribution Playbook by Channel
TikTok > Apple Search Ads > Driving Schools > High Schools > Word of Mouth
Channel | Why It Works | Tactics | Budget | Expected CPI | Best States
TikTok organic content | Teen drivers + parent of teens are on TikTok. Pre-test anxiety = relatable content. | "Questions that trip everyone up" • Fail-compilation reactions • Sign-recognition challenges • Spanish-language teen creator series for TX/CA/FL | $0 (creator time) | $0 | Every state
Apple Search Ads | Direct intent: someone searches "Florida permit test" → high conversion | Per-state keyword sets: "[State] permit test", "[State] DMV practice", "[State] driver test prep" • Bilingual: "examen permiso [estado]" for ES states | $300–1,000 / state launch | $0.50–1.50 | Tier 1 + 2
TikTok paid ads | Reach scale beyond organic. Targeting 16-yr-olds + parents. | Boost top-performing organic. UGC-style only. Avoid polished commercial vibe. | $500–2,000 / state | $1.50–3.00 | Tier 1 + Hispanic-heavy states
Driving school partnerships | Schools recommend the app. Trust transfer + bulk sales. | Free 100-student licenses to first 5 schools per state. School logo in app. Refer-a-school bonus. | Free trial inventory | $0 | Tier 1 + 2
High school driver-ed teachers | Teachers recommend = parents buy. Best free distribution. | Free teacher accounts. Printable lesson plans. State-specific curriculum slides. | $0 | $0 | All states with HS driver ed (most)
Reddit r/[state] communities | Hyperlocal authentic discussion. Cheap if executed honestly. | NOT spam. Genuine help in pre-test threads + organic mention of app. Founder-named account. | $0 | $0 | All states
App Store Optimization (ASO) | Free organic discovery via search rankings. | Per-state app titles: "[State] Permit Test 2026 — DMV Practice". Real reviews. Localized screenshots. | $0 | $0 | Every state
DMV office QR codes | Tactical: hand out flyers near DMV offices in target cities. | Print 1,000 QR-code flyers. Volunteer to hand out at major DMV waiting rooms. | $50 / state | ~$1 | Tier 1 only
Spanish-language radio (TX/CA/FL) | Hispanic immigrant first-time-driver market is huge and underserved digitally. | Drive-time radio sponsorships in Houston, Dallas, LA, Miami. $5/spot reach. | $1,000–3,000 / state | $2–4 | TX, CA, FL
Influencer driving instructors | YouTubers like "Smart Drive Test" have 1M+ subs. Endorsement = trust. | Affiliate code + free pro license. 30% commission per sale. | Revenue share | $0 upfront | All states

## 7. Revenue Projection
Year 1 Revenue Projection (Conservative)
Assumes ~5% paid conversion on installs. Apple takes 30% (or 15% if Small Biz Program qualified).
ASSUMPTIONS (blue = inputs)
Avg paid conversion % | 6%
Apple cut % (30% standard) | 30%
Refund rate | 3%
PER-STATE PROJECTION
# | State | Tier | Price | Est. Installs Y1 | Paid (formula) | Gross Rev | Net Rev
1 | Florida | T1 | 6.99 | 25000 | 1455 | 10170.45 | 7119.315
2 | Texas | T1 | 6.99 | 25000 | 1455 | 10170.45 | 7119.315
3 | New York | T1 | 6.99 | 25000 | 1455 | 10170.45 | 7119.315
4 | California | T1 | 6.99 | 25000 | 1455 | 10170.45 | 7119.315
5 | Pennsylvania | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
6 | Illinois | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
7 | Ohio | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
8 | Georgia | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
9 | North Carolina | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
10 | Michigan | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
11 | New Jersey | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
12 | Virginia | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
13 | Washington | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
14 | Arizona | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
15 | Massachusetts | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
16 | Tennessee | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
17 | Indiana | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
18 | Missouri | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
19 | Maryland | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
20 | Wisconsin | T2 | 5.99 | 8000 | 465.6 | 2788.944 | 1952.2608
21 | Colorado | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
22 | Minnesota | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
23 | South Carolina | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
24 | Alabama | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
25 | Louisiana | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
26 | Kentucky | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
27 | Oregon | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
28 | Oklahoma | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
29 | Connecticut | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
30 | Utah | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
31 | Iowa | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
32 | Nevada | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
33 | Arkansas | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
34 | Mississippi | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
35 | Kansas | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
36 | New Mexico | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
37 | Nebraska | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
38 | Idaho | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
39 | West Virginia | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
40 | Hawaii | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
41 | New Hampshire | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
42 | Maine | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
43 | Montana | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
44 | Rhode Island | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
45 | Delaware | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
46 | South Dakota | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
47 | North Dakota | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
48 | Alaska | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
49 | Vermont | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
50 | Wyoming | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
51 | Washington DC | T3 | 4.99 | 3000 | 174.6 | 871.254 | 609.8778
| TOTAL |  |  | 321000 | 18682.2 | 112313.778 | 78619.6446
SCENARIOS
Scenario | Conv % | Year 1 Net Rev
Pessimistic | 3% | 39309.8223
Conservative (default) | 6% | 78619.6446
Optimistic | 10% | 131032.741
Stretch | 15% | 196549.1115

## 8. Risk Register
Risk Register — Things That Could Kill This
# | Risk | Likelihood | Impact | Mitigation | Trigger / Sign of Trouble
1 | Apple rejects "DMV" or "permit test" naming as misleading | Medium | High | Use precise language: "[State] Driver License Practice Test" not "Official DMV Test." Don't claim official endorsement. Read App Store Review Guidelines 5.4 carefully. | First state submission rejection.
2 | DMV Genie / iDriverManual launch a paid premium tier with no ads | Medium | High | Move fast. Differentiate on multi-language, privacy-first positioning, one-time-purchase. Lock in driving school partnerships. | Competitor adds paid tier in App Store.
3 | State updates handbook mid-year and questions become outdated | High | Medium | Subscribe to state DMV news feeds. Quarterly content review cycle. Push update within 30 days of handbook revision. | User reviews mention "outdated questions."
4 | Spanish/foreign-language translation accuracy issues damage reputation | Medium | High | Use native-speaker translators NOT machine translation. Have 5+ users review per language before launch. Flag user-reported errors as P0 fixes. | 1-star reviews mentioning translation errors.
5 | Driving-Tests.org or competitor sues over question similarity | Low | Critical | Write all questions IN-HOUSE from public domain handbook. Document source for each question. Don't scrape ANY competitor. | Cease-and-desist letter.
6 | Apple Search Ads CPI spikes due to competitor bidding | High | Medium | Diversify channels: TikTok, school partnerships, ASO, organic. Don't depend on Search Ads alone. | CPI > $3.00 sustained.
7 | iOS App Store paid-app market continues declining vs. F2P/IAP | Medium | Medium | Add IAP "Pro" upgrade as a secondary monetization (pricing sheet). Test free-with-IAP variant for one state. | Conversion rates drop quarter-over-quarter.
8 | Florida bilingual study app fails because target users don't use App Store | Medium | Low | Validate with 50 Hispanic FL users via WhatsApp before building. Possibility: target Android instead. | Pre-launch waitlist conversion < 1%.
9 | You spread too thin — ship 4 states badly instead of 1 state perfectly | High | High | Florida MUST hit Gate criteria (>5% paid conversion, 4.5+ stars) before TX work begins. Discipline. | Florida sub-3% conversion or sub-4-star reviews.
10 | A state changes test format unexpectedly (FL English-only mandate) | Medium | Medium | Build content as data, not code. Format changes = data update, not engineering work. | State DMV announces test format change.

## 9. Pre-Launch Checklist
Pre-Launch Validation Checklist (per state)
Run this before submitting any state to App Store. Don't skip.
# | Phase | Check | Pass/Fail | Notes
1 | Content | Question count matches state real exam (e.g. FL=50, TX=30, NY=20)
2 | Content | Pass score matches state (FL=80%, TX=70%, NY=70%)
3 | Content | Real state agency name used throughout (DMV / DPS / DDS / MVA / RMV)
4 | Content | All questions written from public-domain state handbook only
5 | Content | Question accuracy reviewed by 3+ recent test-takers in target state
6 | Content | Translation reviewed by native speakers (not Google Translate)
7 | Content | State-specific fines and laws cited correctly with handbook page reference
8 | Legal | No claim of "official DMV" or state endorsement in marketing copy
9 | Legal | Privacy policy posted at hosted URL (no tracking, no ads, no cloud)
10 | Legal | No question copied from competitor (Driving-Tests.org, DMV Genie, Zutobi)
11 | Tech | App works fully offline (test in airplane mode)
12 | Tech | Audio narration (TTS) works for all questions
13 | Tech | VoiceOver / accessibility labels on every interactive element
14 | Tech | Dynamic Type (text size scaling) supported
15 | Tech | No analytics SDKs / no third-party tracking
16 | Tech | Tested on iPhone SE (smallest screen) and iPad
17 | Marketing | App Store screenshots: 6.7"/6.5"/5.5" sizes + iPad
18 | Marketing | App Store description: clear differentiator (no ads, no subscription, no tracking)
19 | Marketing | Landing page live with screenshots and FAQ
20 | Marketing | TikTok account live with 5+ videos before launch
21 | Marketing | Apple Search Ads campaign drafted with negative keywords
22 | Distribution | 3+ driving schools agreed to pilot
23 | Distribution | High-school driver-ed teacher contact list built
24 | Distribution | Reddit r/[state] community moderators contacted
25 | Quality | TestFlight beta with 50+ users completed
26 | Quality | Average user rating in beta = 4.5+ stars
27 | Quality | <3 critical bugs reported in last week of beta
28 | Business | StoreKit 2 IAP tested in sandbox
29 | Business | Refund-handling logic tested
30 | Business | Pricing tier finalized vs. competitor analysis

## 10. 12-Month Roadmap
12-Month Roadmap
Calendar view of state launches, milestones, decision gates.
Month | Phase | States Live | Engineering Focus | Content Focus | Marketing Focus | Decision Gate
M1 | Tier 1 | FL | Engine + FL content | FL question bank (400 Qs) | FL TikTok seed, ASA test | FL hits >5% paid conv?
M2 | Tier 1 | FL+TX | TX bilingual port | TX question bank + Spanish QA | TX TikTok bilingual | TX same metrics as FL?
M3 | Tier 1 | +CA | Multi-language framework | CA 9-language content | CA driving school partnerships | CA install volume?
M4 | Tier 1 | +NY | NY format port (20 Qs) | NY content + 13-language QA | NYC immigrant outreach | Tier 1 cumulative >$50K?
M5 | Tier 2 | +PA, IL | 2 states / month | PA + IL content | Polish + Spanish targeting | –
M6 | Tier 2 | +OH, GA | 2 states / month | OH + GA content | Atlanta Korean/Vietnamese | Tier 2 unit economics
M7 | Tier 2 | +NC, MI | 2 states | NC + MI (Arabic for MI) | Dearborn Arabic-language | –
M8 | Tier 2 | +NJ, VA | 2 states | NJ multilingual + VA | NoVA tech immigrant | –
M9 | Tier 2 | +WA, AZ | 2 states | WA + AZ | Seattle Russian/Ukrainian | –
M10 | Tier 2 | +MA, TN | 2 states | MA (35+ langs) + TN | Boston multi-lingual push | Decide V2 features
M11 | V2 + T3 | +IN, MO + V2 dev | CDL module dev starts | IN + MO content | Driving school B2B portal | –
M12 | V2 + T3 | +MD, WI + V2 launch | CDL Class A v1 | MD + WI content | Reflect & strategize Y2 | V2 launch decision